## Sheet1
ZEITI IMPLEMENTATION PLAN 2017-2018
Vision Statement | A well Informed, educated and engaged citizenry, prudently utilized mineral resources and equitable socio-economic development.
Mission | To promote transparency and accountability in the governance of the mining sector in order to contribute to sustainable and equitable socio-economic development of Zambia.
Goal | To achieve 100% disclosure of information on the mineral value chain by 2019
OBJECTIVE 1 | To promote full disclosure of information on the mineral value chain in order to enhance transparency and accountability in the governance of the mining sector.
STRATEGY | OUTCOME |  | INDICATORS | ACTIVITY | PLANNING | [7 empty] | ACTORS |  | COST
|  | OUTPUT |  |  | 2017 |  |  |  | 2018
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | LEAD | DONOR
1.1. (i) Engage relevant government institutions and other stakeholders on the development of an Integrated Electronic Information Management System; | 1.1 Reliable and appropriate information on disaggregated employment data captured in the report | a comprehensive template developed and disseminated on disagregated employment reporting by Q4 2017. | 1.1.1. (i) Disaggregated employment data (Zambian citizens, expatriates, gender and skills set) incorporated in the EITI report by 31st December, 2016. | Engage relevant government institutions and mining companies to incorporate disaggregated employment data for the mining sector in the Labour Force Survey for inclusion in the reporting template. | [8 empty] | ZEITI,MUZ,MMMD,CSOs. | GRZ | , | bar: 2017 4
1.2 Engage stakeholders to secure consensus on the development of ZEITI Policy, legislation and Regulations; | 1.2 Influence favorable labour laws and policy in the mining sector | EITI policy develoed by Q2 2018. | 1.1.2 A road map on beneficail ownership developed and implemented by Q2 2017. | Develop the EITI Policy for legal and institutional framework | [8 empty] | EITI,CSOs/MSG | CPs | , | bar: 2017 2
| increased information access | ToR developed by Q4 2017 | 1.2.3 EITI reporting interfaced with Cadasteral | Interface the EITI reporting with the Cadastre | [8 empty] | ZEITI | CPs | , | bar: 2017 4
| enabling legal and policy framework for the EITI process | EITI SI developed on BOD | (1.2.4) Statutory instrument on disclosure issued by 31st May, 2016 | Revise the EITI Bill for legal and institutional framework and hold on-going stakeholder meetings with mining companies | [8 empty] | ZEITI/CSOs | CPs | , | bar: 2017 2
| Increased transparency in the mining industry | MoU developed with ZRA | (1.2.5) Interim Report on the Mineral Value Chain produced by 31st August 2018 (viii) ZEITI reporting template to include tax liabilities and profits reviewed by 31st August, 2017 in collaboration with ZRA | Include tax liabilities, costs and profits in collaboration with ZRA and other relevant authorities in the ZEITI reporting template | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 3
| 1.3 incrased reporting on artisanal mining in the EITI reporting process | MoU developed with LVWP | (1.2.6) The Artisanal Mining Rights reported in the EITI Reports by 31st August, 2017 | Develop partnerships between EITI and UNDP, MMMD Low Value Mineral Development Project (LVMP) | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 4
|  |  |  | Develop partnerships between MVCMP; MPSMP and EITI and the African mining vision | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 4
| 1.4 A comprehensive EITI report for enhanced transparency and credible revenue management used by all stakeholders in policy formulation | 3 workskops held on modified EITI reporting |  | EITI reporting stakeholders engagement | [8 empty] | EITI,CSOs/MSG | GRZ | , | bar: 2017 4
OBJECTIVE 2 | To promote full disclosure of information on the mineral value chain in order to enhance transparency and accountability in the governance of the mining sector.
STRATEGY | OUTCOME |  | INDICATORS | ACTIVITY | 2017 1: PLANNING | ACTORS |  | COST
|  | OUTPUT |  |  | 2017 1: 2017; 2018 1: 2018
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | LEAD | DONOR
2.1. (i) Engage stakeholders to secure consensus on the development of ZEITI Policy, legislation and Regulations | Increased community participation in the planning, implementation and monitoring of CSR programmes and alignment of CSR initiatives to national development priorities | 3 stakeholders consulative workshops held on EITI CSR reporting Q3 2017. | 2.1.1. (i) Five Stakeholder engagement and sensitization workshops and reports on sustainability and community empowerment (Corporate Social Responsibility) programmes being undertaken by the extractive industry held and produced annually. | Participate in the development of CSR guidelines by mining companies, civil societies and other relevant stakeholders | [8 empty] | MSG/CSOs | GRZ | , | bar: 2017 3
|  | 2 community workshops on EITI CSR reporting held by Q2 2018 |  | Community Workshops on CSR EITI reporting | [8 empty] | MSG/CSOs | GRZ | , | bar: 2018 2
|  |  |  | Reasearch conducted on the impact of EITI reporting on CSR payments | [8 empty] | MSG/CSOs | GRZ | , | bar: 2017 4
2.2. (ii) Engage Chamber of Mines and other stakeholders on the development of a Common Strategy for Corporate Social Responsibility (CSR); | Increased community participation in the planning, implementation and monitoring of CSR programmes and alignment of CSR initiatives to national development priorities | 1 CSR stakeholders symposium held by Q2 2018. | 2.2.1.(ii) Percentage increase in the number of community-responsive Corporate Social Responsibility programmes implemented. | 1 natioanal CSR stakeholders Engagement on EITI reporting held | [8 empty] | COM/ZETITI/CSOs |  | , | bar: 2017 2
| Increased community participation in the planning, implementation and monitoring of CSR programmes and alignment of CSR initiatives to national development priorities |  |  | Two worshops held on EITI reporting for CSR spending with CSOs,government and mining companies | [10 empty] | ,
OBJECTIVE 3 | To disseminate information on the Mineral Value Chain and mining sector governance in order to create awareness and stimulate informed decision making. To monitor and evaluate the effectiveness of the Mining sector in order to assess its impact on the socio-economic development of the country.
STRATEGY | OUTCOME |  | INDICATORS | ACTIVITY | 2017 1: DELIVERY PERIOD | ACTORS |  | COST
|  | OUTPUT |  |  | 2017 1: 2017; 2018 1: 2018
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | LEAD | SUPPORT
1.1. (i) Revise ZEITI report format to make it more accessible and make EITI data publicly available through an online portal. | increaseda access to simplified EITI reporting information | 2 comprehensive reports with new accessible format published by 2018. | 1.1.1. EITI reconciliation reports published in a new, more accessible format with the reconciliation report for FY 2016 | EITI reconciliation reports published in a new, more accessible format with the reconciliation report for FY 2017. | [8 empty] | MSG/MOMMD | CPs | , | bar: 2018 1
| comrehevsive EITI access to information for stakeholders | EITI data linked to an online portal by Q4 2018. | 1.1.2. Public access to EITI data via an online portal established at the time the FY 2016 EITI reconciliation report is published. | Public access to EITI data via an online portal established at the time the FY 2017 EITI reconciliation report is published. | [8 empty] | MSG/MOMMD | CPs | , | bar: 2018 3
1.2. (ii) Develop a work program for preparing topical reports on issues relevant for mining sector governance | increased transparenct and acountability in the ETI process | EITI topical report prepared by Q4 2018. | 1.2.1. EITI topical report prepared regularly (annually for 2017/18, with frequency of reports increased thereafter | EITI topical report prepared regularly (annually for 2017/18, with frequency of reports increased thereafter. | [8 empty] | MSG/MOMMD | CPs | , | bar: 2017 4; 2018 4
1.3. (iii) Review the Information, Education and Communication Strategy; | communities making decisions using EITI reports | IEC and Communication strategy reviewd and produced by Q4 2018. | 1.3.1. Information, Education and Communication Strategy (IEC) reviewed by 31st December 2017 with particular emphasis on (a) wider distribution of EITI reconciliation reports and (ii) exploring dissemination synergies with relevant stakeholders | Information, Education and Communication Strategy (IEC) reviewed by 31st December 2017 with particular emphasis on (a) wider distribution of EITI reconciliation reports and (ii) exploring dissemination synergies with relevant stakeholders | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2018 4
|  | 4 staff attain training in EITI website Information Management by Q4 2017. |  | Staff/MSG capacity building including communication skills | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 4
|  |  |  | ZEITI website upgraded and monitored | [10 empty] | , | bar: 2017 4
1.4. (iv) Interface with ZCM to recognize excellence in EITI reporting compliance. | enhenced compliance by mining companies | 2 compliance awards for derserving mining Companies held by Q4 2018. | 1.3.2. Compliance Awards held for Mining Companies every year. | Sensitisation forums on EITI reporting Compliance carried out on the Copperbelt and North-western Province | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2018 4
OBJECTIVE 4 | To monitor and evaluate the effectiveness of the Mining sector in order to assess its impact on the socio-economic development of the country
STRATEGY | OUTCOME |  | INDICATORS | ACTIVITY | 2017 1: DELIVERY PERIOD | ACTORS |  | COST
|  | OUTPUTS |  |  | 2017 1: 2017; 2018 1: 2018
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | LEAD | SUPPORT
2.1. Develop and implement a monitoring and evaluation framework | increased CSO and Community participitaion and decision making | 3 CSO EITI Consultative governanance and Monitoirng Workshop by Q4 2017. | 2.1.1. Monitoring and evaluation framework developed and implemented by 31st January 2019 | 3 EITI Natural Governance Consultative Workshops held in Lusaka,North-western and Copperbelt | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 2; 2018 2
2.2. Compile and disseminate best practices | enhanced socail and ecocomic development | 3 Case Studies devloped on EITI process and its impact on social economic development by Q4 2017 and Q2 2018. | 2.2.1. Reports on best practices produced and disseminated annually | 3 Case Studies on EITI process and its impact on social-economic developemnt developed and documented | [8 empty] | WFC, EITA, CCZ | CPs | , | bar: 2017 3
2.3Develop and implement capacity building programme for CSOs to monitor and evaluate the effectiveness of mining sector governance (1.2.7) Five Stakeholder sensitisation and engagement workshops held and reports produced annually. | enhanced participation and decision making and soace created for Civil Society | 2 CSO monitoring and evaluation held in North -western and Copperbelt Province by Q3 and Q3 of 2017 and 2018 respectively. | 2.3.1Thirty representatives of CSOs trained in Monitoring and Evaluation annually | 1 Comprehensive CSO EITI Community Monitoring and Evaluation framework developed and implemented | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 2
|  |  |  | TOR for CSO EITI M&E developed | [10 empty] | ,
OBJECTIVE 5 | To manage the operations of the ZEITI Secretariat in order to ensure efficiency and effectiveness in the implementation of programmes.
STRATEGY | OUTCOME |  | INDICATORS | ACTIVITY | 2017 1: DELIVERY PERIOD | ACTORS |  | COST
|  | OUTPUTS |  |  | 2017 1: 2017; 2018 1: 2018
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | LEAD | SUPPORT
3.1.Develop and implement an Integrated Management Information System; and | Enhanced EITI information management and Utlisation | IMIS developed and implemented by Q2 2018 | 3.1.1. Integrated Management Information System established and operational by 31st January 2017; | Consultant engaged to develop the IMIS for ZEITI | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2018 2
|  |  |  | IMIS launch | [10 empty] | ,
3.2. Develop and implement capacity building programme on the use of the Integrated Management Information System; | Enhanced EITI information management and Utlisation | IMIS developed and implemented by Q2 2018 | 3.2.1. Relevant stakeholders trained in the use of the Integrated Management Information System by 30thJune, 2017; | ZEITI staff and MSG trained in IMIS | [8 empty] | MSG/ZEITI | GRZ | , | bar: 2017 2
|  | 2 Consultative Workshops held with Mining Companies on the Cpperbelt and Noth-Western Province |  | Dissemination Workshop for Mining Companies on the IMIS | [8 empty] | ZEITI/ZCM | GRZ | , | bar: 2017 3
3.3. Institutionalize the performance management package; | Enhamced Staff Performance for EITI staff and delivery of Work | EITI staff intergrated in government performance management system | 3.3.1. 100% of staff appraised by 31st December of each year | 2 Consultative meetigs with the MOMMD held on ZEITI Staff Performance Package | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 4; 2018 4
3.4. Develop and implement a staff training plan; | Enhanced Capacity Development for EITI Staff | ZEITI staff Capacity Development Manual developed and implemented by Q4 2017. | 3.4.1Training Needs Analysis conducted and Training Plan developed by 31st December, 2016;Staff to receive on average 14 days or training/year starting in FY 2017 | 1 Staff needs assessment conducted | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 2
|  |  |  | Staff/MSG attend training on project management and resource mobilisation and other relevant capacity building needs. | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 2
3.5. Develop an implementation plan for the 2016-2020 Strategic Plan; | Timely and Quality implementaion of EITI activities | ZEITI Implementation work plan developed and implemented by Q4 2017. | 3.5.1. Implementation plan for the 2016-2020 Strategic Plan developed by September 15, 2016 | Develop the ZEITI Implementation Plan in line with the a 2 year mandate of the strategic plan. | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 2
3.6. Review and implement a resource mobilization plan; | increased financiial resources for implementing the EITI Strategic Plan | Revised resource mobilisation strategy developed and implemted by Q2 2018. | 3.6.1. Resource mobilisation plan developed by Q4 2017. | Review the resource mobilastion | [8 empty] | MSG/MOMMD | GRZ | , | bar: 2017 3
|  |  |  | Launch the resource mobilisation strategy | [8 empty] | MSG/MOMMD | GRZ | ,