## sheet1 -1
Zambia EITI Workplan - 2014-2016
Objective 1: | Move towards full adoption of EITI Standard by end of 2014
Activity | Actions | Responsible party | Timeline | Constraints | Actions to address constraints | Cost (US$) | Funding sources | Status*
Production of 2012-2013 ZEITI Reports | Produce TORS for producing the 2012 and 2013 Reconciliation reports, in line with EITI Standard | ZEC | April 2014 | n/a | Addressing government to pass the policy | n/a | World Bank | In progress
| Prepare tender/bidding documents | ZEC | May-July 2014 | n/a | n/a | n/a | n/a | In progress
| Selection of Independent Administrator to prepare 2012 and 2013 Reconciliation Reports | ZEC | June-July 2014 | n/a | Expedite the process of preparing the TORs and consulting the International EITI Secretariat | n/a | n/a | In progress
| Development and adoption of updated reporting template | ZEC | 2014-06-01 | n/a | n/a | n/a | n/a | Awaiting appointment of Independent Administrator
| Produce accurate production and mineral sales figures from Government | Independent Administrator/MMEWD/BOZ | TBD | Unreliable data and unclear processes | Engage relevant stakeholders to produce synchronized data | n/a | n/a | Awaiting results from the appointed committee under ZRA/MMWED
| Document results from gemstone auctions in reconciliation reports | Independent Administrator/MMEWD/companies/ZRA | TBD | Unavailability of data | Engage relevant stakeholders to make information available and accessible | n/a | n/a | Awaiting establishment of gemstone trading platform
| Gather information on beneficial ownership of extractive companies(provide an internet link where such data can be accessed) | ZEC/Independent Administrator | JAN-MAR 2015 | Lack of disclosure | Publishing information and disclosure | TBD | Donors/GRZ | Pilot phase
| Begin preparation of contextual summaries for 2012-2013 Reports, ahead of Independent Administrator if necessary: | ZEITI Secretariat | May-July 2014 | No central repository of contextual information | Engagement with relevant GRZ Agencies to collect information for publication in 2012-2013 ZEITI Reports | Included in cost of producing reconciliation reports | Donors/GRZ | Ongoing
Full license registry (3.9)
License allocation process (3.10)
Beneficial ownership (3.11&3.6)
Copies of all active MDAs (3.12)
Current exploration activities (3.3)
Total production figures (3.5)
Total exports (3.5)
Legal framework and fiscal regime (3.2)
Economic contribution (3.4)
ZCCM-IH activities and ownership (3.6)
Subnational payment policies (4.2)
Mining sector employment statistics (3.4)
Revenue Management policies (3.8)
Establish and maintain the Zambia EITI database to expedite future reporting under EITI | Collect all previous reporting templates from 2008-2011 ZEITI Reports, and convert to digitial (i.e. Excel) format | ZEITI Secretariat | May - August 2014 | n/a | n/a | n/a | n/a | TBD
| Draft the TORs for the consultant to establish the Zambia EITI database | ZEC | 2013 | n/a | n/a | n/a | n/a | done
| Appoint a selection committee/prepare and evaluate tender/bidding documents | ZEC | 2013 | n/a | n/a | n/a | n/a | done
| Establish the real time data base for the Zambia EITI | ZEC | 2015 | Funding | Discussion with the DFID on possible support underway | 2000000 | Donors | In progress
| Intergrate the Zambia EITI database with other relevant government databases and extractive companies | ZEC | JAN-FEB | n/a | n/a | 30000 | Donors | not done
| Undertake learning visits to countries that have implemented the real time data base reporting | ZEC | FEB | n/a | n/a | 60000 | GRZ | done
Enact Zambia EITI Bill as law | Make presentations to various select committees on the draft ZEITI Bill | ZEC | 2014 | n/a | n/a | TBD | GRZ/Donors | not done
| Organise sensitisation meetings on the ZEITI Act among all stakeholders | ZEC | 2014 | n/a | n/a | TBD | GRZ/Donors | not done
To expand the Zambia EITI scope to include discussion of non-revenue issues | Provide a forum for discussion of non-revenue issues such as tax evasion, transfer pricing,environmental degradation, etc | ZEC/OECD | JAN-DEC | Lack of credible information | Collaborating with other institutions in the sector | n/a | n/a | In progress
| Conduct joint awareness raising workshops in areas where extractive companies operate | ZRA/CSOs/MMEWD/MoF/BoZ/Chamber of Mines | JAN-DEC | Lack of credible information | Collaborating with other institutions in the sector | n/a | n/a | In progress
Other initiatives to increase revenue transparency within Zambia | Support mine audits and tax studies to ensure tax compliance by mining companies and also prudent tax management by the government | MMEWD/ZRA/CSOs/OECD/IMF/Revenue Watch | JAN-DEC | lack of capacity within ZRA,MMWED and local CSOs as well as funding to relevant organizations | OECD building capacity for ZRA, MMEWD | 215000 | GRZ/Donors | Mining audits currently being undertaken by ZRA
Objective 2: | To contribute towards enhanced accountability and transparency in the management of revenue collected from the extractive industries.
Activity | Actions | Responsible party | Timeline | Constraints | Actions to address constraints | Cost (US$) | Funding sources | Status*
Promote transparency and accountability in the use of revenue from the extractive sector. | Prepare TORs for the drafting of the Resource Use Policy ( Oil, Gas, Minerals and revenue from non-extractive sectors) | ZEC/MoF/CSOs | JAN-APR | Lack of policy | Addressing government to pass the policy | n/a | n/a | not done
| Engage a consultant to draft the proposed Resource Use Policy | ZEC | JAN-DEC 2015 | Funding | Funding proposals to be sent | TBA | GRZ/Donors | not done
| Organise stakeholder meetings to discuss the finding of the draft Policy | ZEC | JAN-DEC 2015 | n/a | n/a | TBA | TBA | not done
| Engage with the relevant government institutions to ensure the Policy is enacted/passed | ZEC | JAN-DEC 2015 | n/a | n/a | TBA | TBA | not done
Objective 3: | To create public awareness of EITI implementation in Zambia.
Activity | Actions | Responsible party | Timeline | Constraints | Actions to address constraints | Cost (US$) | Funding sources | Status*
Enhance public awareness of EITI in Zambia | Coordinate and conduct television, radio and print-based discussions on the findings of the 2011 and future reconciliation reports | ZEITI Secretariat | Throughout 2014 | n/a | n/a | n/a | n/a | In progress
| Conduct stakeholder workshops to disseminate the findings of the 2011 Report | ZEITI Secretariat | May - June 2014 | Unavailability of funds | Funding application sent | TBD | TBD | In progress
| Conduct community meetings in 10 provinces to discuss revenue and non-revenue issues affecting communities in areas where extractive industries are located | ZEITI Secretariat | 2014 & 2015 | Unavailability of funds | Funding application sent | TBD | TBD | In progress
| Re-launch quartlerly ZEITI newsletter for publication on ZEITI website and in printed format | ZEITI Secretariat | May - June 2014 | Unavailability of funds | Funding application sent | TBD | TBD | In progress
| Disseminate the 2012 and 2013 Reconciliation reports on the Zambia EITI website and also the international EITI website | ZEITI Secretariat | 2014 & 2015 | n/a | n/a | n/a | n/a | Not done
| Publish the 2012 and 2013 Reconciliation reports in the newpapers and other media | ZEITI Secretariat | 2014 & 2015 | n/a | n/a | n/a | n/a | Not done
| Produce branding materials for the Zambia EITI to be used during the dissemination of the 2012 and 2013 Reconciliation reports | ZEITI Secretariat | 2014 & 2015 | Unavailability of funds | Funding application sent | TBD | TBD | Not done