## 2025 ZEITI Work plan
|  | [Zambia] [2025] EITI Work plan |  |  |  | Deliverable status categories | Complete
On track for delivery by agreed timeline
| Approved : [21/11/2024] | [5 empty] | Medium risk - not on track for delivery
High risk - not on track for delivery
Last updated: [08/05/2025]
Monitoring
Objective (Ultimate Outcome) | Rationale: Governance challenges and links to national priorities | Activity No. | Activities | Output | Outcomes (Immediate and Intermediate) | Responsible party | Timeline | Budget Cost (ZMW) | Actual Cost - YTD (ZMW) | Funding source | Key deliverable | Status | Status details/Description | Comments from stakeholders (describe who) | Adjustments to work plan and implementation
|  | 1 | MSG Governance
To promote transparency and accountability in the use of Zambia's natural resources to the benefit of all citizens. | Improved collaboration and networking among the three stakeholders ( Government , industry, CSOs) | 1.1 | Quarterly and emergency MSG Meeting | Minutes of MSG meetings/Reports from Secretariat/Updated Membership/Conference Report | Strengthened EITI implementation Improved MSG participation and coordination | ZEITI/MSG | Q1 - Q4 | 60000 | 19075.81 | GRZ | Minutes of meetings |  | Ongoing
|  | 1.2 | Monthly update of activities from the Secretariat to the MMMD |  |  |  | Q1 - Q4 | 0 | 0 |  | Reports |  | Ongoing
|  | 1.3 | Review and update existing ZEC membership |  |  |  | Q2 - Q3 | 0 | 0 |  | New MSG Members |  | Ongoing
|  | 1.4 | Participation at EITI conferences and other Stakeholder meetings. |  |  |  | Q2 - Q3 | 297582 | 89644.04 |  | Reports |  | Ongoing
|  | 2 | Capacity Building
| To enhance the capacity of MSG/Secretariat in accessing funds for the management of the secretariat, to be able to apply the 2023 Standards, and understand the new validation model through refresher training. | 2.1 | Capacity building for reporting entities | Training reports/Workshop reports/ Staff performance appraisal report, evidence of written proposals | Addressing capacity gap amongst constituency members | ZEITI/MSG | Q1-Q2 | 150000 | 0 | GRZ | Training Report |  | Not started
|  | 2.2 | Capacity building worskshop for new officers in the MMMD on EITI processes |  |  |  | Q2- Q3 | - | 0 |  |  |  | Not started
|  | 2.3 | Capacity building for ZEC members on the validation against the 2023 EITI Standard |  |  |  | Q2 - Q4 | 0 | 0 |  |  |  | Ongoing |  | Workshops was hosted by the International Secretariat
|  | 2.4 | Participation at Extractive Industries related workshops and trainings |  |  |  | Q1-Q4 | 92000 | - |  |  |  | Ongoing
|  | 3 | Gender Mainstreaming
| To scale-up inclusivity and participation of women in the extractive sector | 3.1 | Encourage MSG members to take into account Gender balance as they renew their MSG membership. | Training reports, Minutes of meetings, Annual EITI Report, statistical report | Promote inclusiveness & gender equality/Access to information on women in mining companies. | ZEITI/MSG | Q1 - Q2 | - | 0 | GRZ | Increase in the number of women servig on the ZEC |  | Ongoing
|  | 3.2 | Request reporting entities to disclose employment data disagregated by Gender |  |  |  | Q2 - Q4 | - | 0 |  | Increase in women's employment in the sector as reported in the Annual EITI Reports |  | Not started
|  | 3.3 | Document women's employment statistics by mining companies. |  |  |  | Q1-Q4 |  | 0 |  |  |  | Not started
|  | 4 | Environmental Engagement
| To help promote, protect and preserve the impact of climate change on the environment. To mitigate climate impact /build resilience to it through promotion of climate actions. | 4.1 | Engage the relevant Government Ministries and Agencies for the review of environmental impact policies in line with EITI Standard, and document the impact of mining activities on the environment. | Engagement meeting report/ Annual ZEITI Report/Annual EPF Report. | Improved disclosure on environmental impact/Increase knowledge on the provisions in the environmental & extractive policies. | MSG/ZEITI | Q2 - Q3 | - | 0 | GRZ | Enhanced EITI Report on Environmental Protection Fund management. |  | Not started
|  | 4.2 | Report on the management of the Environmental ProtectionFund. |  |  |  | Q3 - Q4 | 0 | 0 |  |  |  | Not started
|  | 5 | ZEITI Validation corrective actions
| The need for government commitment to fully implement the EITI report recommendations. | 5.1 | Meet MSG members to develop strategies to address Validation corrective actions and recommendations of the 2021-2023 ZEITI Report. | Minutes and Report of meetings, documented strategy in place. Engagement meeting minutes. | Improved implementation of EITI Requirements | ZEITI/MSG. | Q1 - Q3 |  | 0 | GRZ | Completed Validation templates |  | Ongoing
|  | 5.2 | Meet with relevant Government Ministries and Agencies to develop strategies to address Validation corrective actions and recommendations of the 2021-2023 ZEITI Report. |  |  | ZEITI/MSG/MMMD | Q2 - Q4 |  | 0 |  | Publication Corective Actions on the ZEITI website. |  | Not started
|  | 6 | Budget Needs Assessment of operations
| Actualisation of Government's total commitment in the allocation of resources to the EITI process in Zambia | 6.2 | Establish partnership with Donors to support EITI implementation in Zambia | Donor support/Audited Financial Statements | Improved financing and financial managemnt of ZEITI | ZEITI/MMMD/Office of the Auditor General | Q1 - Q2 | 0 | 0 |  | Minutes of meetings |  | Ongoing
|  | 6.3 | Annual audit of activities by the Office of the Auditor General and the MMMD Internal Audit Department |  |  |  | Q2 - Q3 | 0 | 0 |  | Internal and External Audit Report |  | Ongoing
|  | 7 | Annual Report Production
| To enhance transparency and accountability, and strengthen public awareness and participation | 7.1 | Develop Terms of Reference for the Independent Administrator to be approved by MSG | Tracking & disclosure of funding | Effective management of implementation | ZEITI/MSG | Q1 - Q2 | 0 | 0 | GRZ | Approved ToRs. |  | Not started
|  | 7.2 | Advertise & recruit Independent Administrator | Annual EITI Report produced | Increased and timely disclosure of extractive sector information | ZEITI/MSG/IA | Q2-Q3 | - | 0 |  | Scoping, Inception and Final Reports and publication on ZEITI website |  | Complete
|  | 7.3 | Data collection for the production of the 2024 ZEITI Report |  |  |  | Q1-Q4 | 420000 | 331116.54 |  |  |  | Not started
|  | 7.4 | Production and publication of the 2023 and 2024 reports on ZEITI website |  |  |  | Q2 - Q4 | 600000 | 0 |  |  |  | Not started
|  | 7.5 | Produce summary data template for 2023 and 2024 Report |  |  |  | Q4 | 0 | 0 |  |  |  | Not started
|  | 8 | Mainstreaming EITI Data
| To disclose accurate and real-time mining sector related data effeciently. | 8.1 | Support towards the ZEITI Mainstreaming Portal | EITI mainstreamed. Public online disclosure of EITI related data. | 06J60 | Relevant MDA/Industry | Q1 - Q4 | 140000 | 0 | GRZ | Enhanced transparency within the extractive sector |  | Not started
|  | 8.2 | Encourage key institutions to systematically disclose all EITI related data (production, export, revenue, subnational payments and transfers, licenses award and contracts) on a publicly accessible government website/portal in both human and machine-readable formats. |  |  |  | Q1 - Q4 | 0 | 0 |  |  |  | Ongoing
|  | 9 | Beneficial Ownership Disclosure
| Ensure full compliance with BO policy. | 9.1 | Work with key agencies (MMMD, PACRA, FIC) to map out strategies on a national approach to BO implementation. | Minutes, Reports, Recommendations | Strengthened Accountability | ZEITI/MSG/PACRA/FIC | Q2 - Q3 | - | 0 | GRZ | Improved BOT |  | Not started
|  | 9.2 | Advancing BOT through stakeholder dialogue, engagement and capacity building |  |  |  | Q2 - Q3 | 42000 | 0 |  |  |  | Not started
|  | 10 | Energy Transition
| Promote transparency and accountaibility in the Energy Transition through publication of data and information pertaining to the energy transition e.g PPAs | 10.1 | Engage relevant Ministries and Agencies (ZESCO/ERB)on government national energy transition commitments, policies and plans. | Engagement minutes, Energy Transition policies/plans/Annual EITI Report | Strengthened Accountability | ZEITI MSG/Energy for Growth HubMMMD | Q2 - Q3 | 2000 | 0 | GRZ | Comprehensive Government plan and policies on the Energy Transition. |  | Ongoing
|  | 10.2 | Engage companies to disclose greenhouse gas (GHG) emissions in alignment with existing disclosure standards. |  |  |  | Q2 - Q4 | 2500 | 0 |  |  |  | Not started
|  | 10.3 | MSG to document socio-economic opportunities, risks and governance challenges of energy transition |  |  |  | Q3 - Q4 | 1000 | 0 |  |  |  | Not started
|  | 11 | Anti-corruption
| Enhance transparency & accountability in the implementation of EITI process & standards | 11.1 | Engage the Anti-corruption Commission (ACC) to serve as a member of the Zambia EITI Council. | ACC serving on the MSG/Annual EITI Report/ Minutes of MSG meetings | Strengthened Accountability | ZEITI/MSG/ACC | Q2 - Q4 | 0 | 0 | GRZ | Comprehensive Anti-Corruption strategy on the extractive sector. |  | Not started
|  | 11.2 | Identify and document corruption risks related to extractive sector governance. |  |  |  | Q2 - Q4 | 0 | 0 |  |  |  | Not started
|  | 12 | Enhanced ZEITI visibility and Impact on EITI Implementation
| To promote transparency in all aspects of the extractive sector | 12.1 | Outreach and Dissemination Workshops for EITI Reports | Reports/News broadcast/Analytics report | Improved citizens participation in all aspects of SLEITI implementation | ZEITI MSG | Q2 - Q4 | 310000 |  | GRZ | Increased availability of EITI data and knowledge of the sector. M&E report on Media analysis |  | Not started
|  | 12.2 | Consultancy to prepare the 2025-2030 ZEITI Communications StrategY |  |  |  | Q3 - Q4 | 130000 | 0 |  |  |  | Not started
|  | 12.3 | Hosting, upgrade & improve user interface of the ZEITI website |  |  |  | Q2 |  | 128546.49 |  |  |  | Completed
|  |  | Total |  |  |  |  | 2247082 | 568382.88